YAMADA 2021 PROJECT REPORT

IBBY GHANA

Capacity Building in Basic Library Management and Reading Promotion Skills for Primary School Teachers in Assin Nkran, Central Region, Ghana, to Assist in Improving Children’s Literacy Levels.

- Overview

| Category: | Category A |
| --- | --- |
| Project Title: | Capacity Building in Basic Library Management and Reading Promotion Skills for Primary School Teachers in Assin Nkran, Central Region, Ghana, to Assist in Improving Children’s Literacy Levels. |
| Implementing Partner: | IBBY Ghana |
| Country: | Ghana |
| Period of Reporting: | 6 months 31/05/2021- 31/11/2021 |
| Date of Submission: | 20/12/2021 |
| Summary of the Report: | Project Activities and Evaluation of the Project |

- Introduction

IBBY Ghana received funding to implement the Yamada 2021 Project in February 2021. The IBBY Ghana/Yamada 2021 project aimed at improving the capacity of 40 teachers in Assin Nkran in the Central Region of Ghana by providing training in Basic Library Management and Reading Promotion Skills. Twenty Schools received 200 books each to enhance their existing library stock. The intervention would help improve children’s literacy levels in the community.

Dates were set for the implementation of the project for March 2021 but due to the second wave of the COVID-19 Pandemic and restrictions on numbers permitted to meet, the implementation of the Project had to be postponed.

Basic education is mandatory for all children in Ghana. However, the 2015 Early Grade Reading Assessment (EGRA) revealed that by the end of Primary 2, the majority of pupils in public schools, battle with foundational reading skills and are not able to read with comprehension – either in a Ghanaian Language or in English.  Sustainable Development Goal 4 states: Ensure inclusive and equitable quality education and promote lifelong learning opportunities for all.  The training workshop was to contribute to the achievement of SDG 4.

The emphasis in public schools has been on textbooks and passing of exams. Many schools lack reading books and teachers lack the skills on how to use reading books to improve reading.  They also lack the know-how so much needed

to create a welcoming and inspiring reading environment that will support children’s interest in reading. In order to give them a better future, children should be able to read for pleasure and enjoyment.  Illiteracy can be minimised by giving educators the knowledge needed to influence children and develop a culture of reading in classrooms and in communities.

- Expected Outcomes of the Project

- Increased capacity of teachers in reading promotion skills

- Better organised and properly functioning school libraries

- More children experiencing the joy of reading leading to the creation of a reading culture with prospects of a better future.

- Project Activities

The implementing team undertook the following activities and completed them successfully.

- The donation of 200 new storybooks to each of the 20 schools is to benefit children aged between. between 3 and 16 years. The donation of books was to create access to more reading materials for children in the community, giving them the opportunity to develop a love for reading.

- A two-day training workshop for 40 teachers in Library Management and Reading Promotion. The workshop was to provide teachers with the basic knowledge to create a welcoming reading environment and inspire children to become life-long readers, who read for leisure as well all as for utilitarian purposes.

- Indicators

- Properly processed and organised library books

- Library periods adhered to and reading promotion activities held.

- Increase in library usage

- Improvement in children’s assessment records

- Project Constraints

The Covid-19 Pandemic affected the implementation of the project within the original timeframe.  There was a disruption in the school calendar.  School were closed down in March 2020 and re-opened in early6 January 2021.  Teachers were more focused on completing the syllabus in the short time they had, than in working on ways to get the children to read. Children were also loaded with work to make up for time spent at home and in order to complete the syllabus in time for the next batch of children to come in. That was the kind of environment that existed during the Project implementation and affected the outcomes within the timeframe envisaged.

- Baseline Survey Results

A baseline survey indicated that there was a need for more reading books and for increased awareness among both teachers and children of the importance of reading. Capacity building for teachers was also needed in the area of reading promotion.

Andoe D/A Basic B, Assin Domeabra D/A Basic, Nkran Ngresi Basic A & B and Asamankese D/A Primary & JHS had 100% passes in English, The total number that sat for the exam in Nkran Ngresi B was unknown. Manso D/A Primary B Basic had 77.10%

| NAME OF SCCHOOL | Percentage of Students who passed English | Number of students who sat for 2019 BECE |
| --- | --- | --- |
| Andoe D/A Basic 'B' School | 100% | 28 |
| Manso D/A Primary 'B' Basic School | 77.10% | 35 |
| Assin Domeabra D/A Basic School | 100% | 11 |
| Nkran-Ngresi Basic 'B' School | 100% |  |
| Nkran-Ngresi Basic 'A' School | 100% | 44 |
| Asamankese D/A Primary & JHS | 100% | 41 |

- Evaluation

The evaluation of the Project took place in the month of November 2021 and aimed at assessing improvements in the reading skills of children in the Project schools, as well as monitor the progress of teachers in Library Management and Reading Promotion.

Objectives for the Evaluation

- To evaluate the accessibility to donated books.

- To assess if techniques taught at the workshop were being implemented by teachers.

- To assess the reading skills of Primary and JHS pupils/students.

- To gain feedback from teachers and Head Teachers about the reading progress of pupils/students, challenges and comments on training held.

1. Field Survey

1.1. Sampling Methodology

1.1.1 Total Population:

The total population for this project consisted of 20 schools and 40 teachers in Assin Nkran in the Central Region of Ghana.

1.1.2.  Sample Size and Allocation:

Six schools in Assin Nkran were selected for the evaluation.

Three main groups were sampled. They were:

- Pupils

- Teachers

- Head Teachers

  - 3.  School and Class Eligibility

Class 4 was selected as the lowest class for the evaluation because the medium of instruction from Classes 1 to 3 is the local language with English as a subject, so pupils/students were not very conversant with reading and writing in the English. Language.

Forty-eight (48) pupils/students were randomly selected from Classes 4,5, 6, and JHS 1 for the evaluation. Six Teachers and six Head Teachers were interviewed.

- Methodology

To assess the level of improvement in the reading skills of pupils in the schools, a mixed approach was used.  A probability sampling technique was employed, where members of the population all had equal chances of being selected. This enabled the evaluators to have a fair idea of the reading performance of the whole population. The probability sampling technique used was the systematic sampling technique.

A reading assessment was designed to assess participants in fluency, comprehension, letter and sound recognition and vocabulary. Pupils were required to read short passages selected for the various class levels and to answer questions from the passage. The survey comprised an equal number of male and female pupils and the key informants were the teachers and the Head Teachers in each school.

A questionnaire was developed for Head Teachers, while teachers were interviewed about the books donated and pupils’/students’ performance in reading.

The sample size of 8 pupils per school was calculated based on the number of personnel and the time available to conduct the evaluation.

- Findings

1.0 DEMOGRAPHICS

|  | NAME OF SCHOOL | POPULATION RANGE | NO. OF PUPILS/STUDENTS IN A CLASS | RATIO OF BOYS TO GIRLS | AGE RANGE | ACCESSIBILITY TO BOOKS |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Assin Domeabra D/A Basic | 101-250 | 40+ | 114:121 | 6-15 | Head Teacher’s office and selected room for the library |
| 2 | Nkran-Ngresi D/A Basic A | 251-500 | 34 | 17:17 | 9-15 | Shelves in the library |
| 3 | Asmankese D/A Basic | 51-100 | 43 | 1:1 | 9-12 | School library |
| 4 | Andoe D/A Basic B | 501+ | 60 | 25:35 | 12-15 | Storeroom |
| 5 | Assin Nkran-Ngresi D/A Basic B | 101-250 | 58 | 31:27 | 10-16 | On shelves |
| 6 | Assin Manso D/A Basic B | 251-500 | 50+ | 112:150 | 8-12 | Staff common room |

3.0 PROJECT INDICATORS

3.1 Processing and organisation of Books.

During the baseline survey assessment, it was gathered that schools did not have a designated area where pupils/students could have access to books. During the evaluation, all schools had a storeroom for the books or an established library. Books were processed and there were records of books borrowed by pupils/students.

Processed book by Assin Manso D/A Basic

Asamankese D/A Basic School designated room set aside for reading after the workshop

Organised books on the shelves of Andoe D/A Basic School

Library Records of Nkran Ngresi ‘A’ Basic School; usage of books began after workshop.

3.2 Library Periods and Reading Promotion Activities

Library periods data before the workshop.

The baseline survey indicated that Assin Domeabra D/A Basic School had two (2) library periods per week, while Andoe D/A Basic B, Nkran-Ngresi A & B had one library period per week and Manso D/A Primary B Basic and Asamankese D/A Primary & JHS had no library periods. However, during the evaluation after the library management and reading promotion workshop, all schools now have library periods and are engaging in reading promotion activities to motivate pupils/students to read.

Library period data after the workshop.

Reading Tree in Class 5 of Nkran Ngresi A Basic School

-

A reading motivation corner in class 5 in Assin Nkran; motivational strategy developed after the training.

Asamankese D/A Basic School pupils reading during the library period

New words gotten from Assin Manso Basic School library period.

3.3 Library Usage

There has been a significant increase in the usage of libraries in all schools.  Pupils/students are allowed access to the library during school hours. Pupils/students are allowed to borrow books home.

Pupils utilizing the library during their break time.

4.0 COMPARISON BETWEEN BASELINE ASSESSMENT AND READING SURVEY ASSESSMENT

Eighty students were assessed during the evaluation and graded based on their Fluency, Comprehension, Spelling and Pronunciation in English. The levels ‘Excellent’, ‘Very Good’, ‘Good’, ‘Okay’ and ‘Not Good’ were the grading schemes. ‘Excellent’ means exceptional performance, ‘Very Good’ is above average performance, ‘Good’ is average performance, ‘Okay’ is a pass, ‘Not Good’ is below average performance. In the baseline survey teachers selected from the levels stated above as a true representation of the Fluency (Spoken English), Spelling (Written English) and Comprehension (Understanding of English). To compare the baseline assessment and the reading assessment the percentage range from 50% and below was used as the standard for assessment. For a fair, range between values 1% was subtracted from 50% to result in 49%, hence a 10% difference from each range. The ranges and corresponding levels are as follows:

40%-49% = Excellent

30%-39% = Very Good

20% - 29% = Good

10% - 19% = Okay

0% - 9% = Not Good

4.1 PUPILS PERFORMANCE IN FLUENCY

ANALYSIS

In Fluency 50% of the schools maintained their levels while the other 50% improved on their Fluency performance.

4.2 PUPILS PERFORMANCE IN SPELLING

ANALYSIS

In Spelling, 33% of the schools improved on their performance after the workshop, whiles 67% maintained their performance in Spelling.

4.3 PUPILS PERFORMANCE IN COMPREHENSION

ANALYSIS

In Comprehension, 50% of the schools dropped in their performance, 33% maintained their comprehension performance whiles 17% of the schools improved on their performance. Also, from the baseline survey it was gathered that pupils/students understood what they read but from the comprehension assessment, it proves pupils/students do not understand what they read in English.

4.4 PUPILS PERFORMANCE IN PRONUNCIATION

5.0 CONCLUSION

In conclusion, there has been a positive impact on the reading of pupils/students in Assin Nkran. All schools have library periods, pupils/students are passionate about reading, books are organised either in a library or storeroom and teachers are engaged in various reading promotion activities with pupils/students.  However, the impact of the library usage and reading promotion activities are yet to affect significantly the pupils’/students’ assessment records.  Even though, the baseline survey indicated a 77% - 100% pass in English in the BECE and some schools have also improved and others maintained their performance, there is still more room for improvement.

Many in the Project schools were previously unaware of the role a school library should play; how a school library should function to make the necessary impact on the educational development of pupils/students, and the role of the teacher in motivating reading. Teachers now have increased capacity, are fully implementing what they were taught during the workshop, so, are seeing results.

The framework has been set with increase in books and training and it is hoped that a lot more improvement will be seen given a longer period to observe results.

(Please see Appendix A: for Pictures, Appendix B: for Teachers’ Responses)

APPENDIX A: PHOTOS

PHOTOS OF SCHOOL LIBRARIES

Andoe D.A. JHS Library

The school children were happy to receive new books

Assin Manso Basic B library period

PHOTOS OF MONITORING AND EVALUATION OF THE PROJECT

Interviewing a student

A member of the team interviewing a student

Evaluating a student

More student evaluations

Students being interviewed

Interviews with Head Teachers

Interviews with Head Teachers

WORKSHOP PHOTOS

Supplementary readers for the twenty schools

Section of participants, and invited guests

Opening ceremony with the Deputy Minister for Education, District Director of Education and IBBY Ghana Executives

The Deputy Minister for Education; President and Treasurer of IBBY Ghana

Arrival of the Representative of the Paramount Chief of Assin Nkran

Workshop Sessions begin

Slides

Workshop Sessions

Cross section of the participants (teachers)

Facilitating a session of the workshop

Practical lesson

Participants dramatizing a story

Facilitating a workshop session

APPENDIX B   Teachers Responses

  - Pupils’/Students’ accessibility to books

- Can children borrow books and take home to read?

- Yes. (Stephen Tetteh, Librarian, Asamankese D/A).

- Yes. Francis Amoah, Assin Manso D/A Basic B, Head Teacher)

- Yes. (Francis Cobbinah, Anyinabrim Catholic Basic, Assistant, Head Teacher).

- Yes. (Isaac Zikpi, Andoe D/A Basic B Head Teacher).

- Yes. (John B Tawiah, Assin Nkran-Ngresi D/A, Head Teacher).

- Yes. (Joseph Ato Yankson, Assin Domeabra D/A Basic, Head Teacher).

- If yes, how many books are they allowed to take home at a time?

- Only One. (Joseph Ato Yankson, Assin Domeabra D/A Basic, Head Teacher).

- A book at a time. (John B Tawiah, Assin Nkran-Ngresi D/A, Head Teacher).

- One at a time. (Isaac Zikpi, Andoe D/A Basic B Head Teacher).

- One at a time. (Francis Cobbinah, Anyinabrim Catholic Basic, Assistant, Head Teacher).

- One book. (Francis Amoah, Assin Manso D/A Basic B, Head Teacher.)

- One (1). (Stephen Tetteh, Librarian, Asamankese D/A).

- How many days can pupils/students keep the books before returning them?

- Five days (5) (Stephen Tetteh, Librarian, Asamankese D/A).

- Sometimes one week. (Francis Amoah, Assin Manso D/A Basic B, Head Teacher.)

- Two weeks. (Francis Cobbinah, Anyinabrim Catholic Basic, Assistant, Head Teacher).

- At least a week. (Isaac Zikpi, Andoe D/A Basic B Head Teacher).

- One day. (John B Tawiah, Assin Nkran-Ngresi D/A, Head Teacher).

- Three (3) days. (Joseph Ato Yankson, Assin Domeabra D/A Basic, Head Teacher).

2.Library Use

What are the opening and closing hours for your reading facility?

8:30am-2:00pm each day (Joseph Ato Yankson,Assin Domeabra D/A Basic, Head Teacher).

From 7:30am-2:00pm (John B Tawiah, Assin Nkran-Ngresi D/A, Head Teacher).

From 8:00am -2:30pm. (Francis Cobbinah, Anyinabrim Catholic Basic, Assistant, Head Teacher).

12:30-1:00pm. (Francis Amoah, Assin Manso D/A Basic B, Head Teacher).

8:30am-3:00pm (Stephen Tetteh, Librarian, Asamankese D/A).

Do you have library periods?

No (Stephen Tetteh, Librarian, Asamankese D/A).

Yes (Francis Amoah, Assin Manso D/A Basic B, Head Teacher.)

Yes (Francis Cobbinah, Anyinabrim Catholic Basic, Assistant, Head Teacher).

Yes (Isaac Zikpi, Andoe D/A Basic B Head Teacher).

Yes (John B Tawiah, Assin Nkran-Ngresi D/A, Head Teacher).

Yes (Joseph Ato Yankson, Assin Domeabra D/A Basic, Head Teacher).

3.Reading Promotion Activities

If yes, what kinds of activities take place during this period?

Books are sent to the class for pupils to select at the Primary, whereas those at the JHS are made to visit the selected room for copies. (Joseph Ato Yankson, Assin Domeabra D/A Basic, Head Teacher).

Silent reading (John B Tawiah, Assin Nkran-Ngresi D/A, Head Teacher).

Sometimes we give them the reading books to read. We also do Spelling ‘B’ with the help of the teacher in charge. (Isaac Zikpi, Andoe D/A Basic B Head Teacher).

Pupils read library books silently. (Francis Cobbinah, Anyinabrim Catholic Basic, Assistant, Head Teacher).

We read the books. (Francis Amoah, Assin Manso D/A Basic B, Head Teacher).

If No, when do children get to read the books?

During ‘Early Bird’ session and pupils/students can also borrow to read at homes. (Stephen Tetteh, Librarian, Asamankese D/A).

Have you engaged the children in any reading activities with the books?

Yes.  (Joseph Ato Yankson, Assin Domeabra D/A Basic, Head Teacher).

Yes. (John B Tawiah, Assin Nkran-Ngresi D/A, Head Teacher).

Yes. (Isaac Zikpi, Andoe D/A Basic B Head Teacher).

Yes. (Francis Cobbinah, Anyinabrim Catholic Basic, Assistant, Head Teacher).

Yes. (Francis Amoah, Assin Manso D/A Basic B, Head Teacher.)

Yes. (Stephen Tetteh, Librarian, Asamankese D/A).

If yes, please elaborate

It is normally done on Fridays where those who borrowed books tell their friends about the author, the title of the book or story read. They also communicate the stories or the content to their friends. (Stephen Tetteh, Librarian, Asamankese D/A).

I give the books to the children. I write and explain the keywords to the children. I then read the story to the kids. (Francis Amoah, Assin Manso D/A Basic B, Head Teacher).

We have been printing excerpts from the books to practice what we call ‘Early Bird’ that is a reading period indicated by the Assin South Education Directorate. (Francis Cobbinah, Anyinabrim Catholic Basic, Assistant, Head Teacher).

The teacher in charge gives the books to them during the ‘Silence Hour’/ ‘Early Bird’ period before assembly. (Isaac Zikpi, Andoe D/A Basic B Head Teacher).

Children give a summary of books read and spell words from the books. (John B Tawiah, Assin Nkran-Ngresi D/A, Head Teacher).

The school has instituted Mid-term/semester reading test in all the classes to assess reading abilities and to promote reading as well. There is a Reading Club to sustain pupils’ interests. (Joseph Ato Yankson, Assin Domeabra D/A Basic, Head Teacher).

4.Results from The Training Workshop

What aspects of the training you received at the workshop have you put into practice?

I was taught on how to record books when the children come to borrow. (Francis Amoah, Assin Manso D/A Basic B, Head Teacher.)

Organised school level inset for teachers on library management and reading promotion. In addition, formation of reading club. (Francis Cobbinah, Anyinabrim Catholic Basic, Assistant, Head Teacher).

Reading log, my reading record. (Isaac Zikpi, Andoe D/A Basic B Head Teacher).

‘Find me.’ (John B Tawiah, Assin Nkran-Ngresi D/A, Head Teacher).

Formation of reading clubs to urge the pupils to have fun with reading and to promote reading in the school with the use of the ‘reading log’/’my reading record’. (Joseph Ato Yankson, Assin Domeabra D/A Basic, Head Teacher)

What are your impressions about the books you received?

They are good because they have given the children varieties of books to choose and read. (Stephen Tetteh, Librarian, Asamankese D/A).

They are good books. (Francis Amoah, Assin Manso D/A Basic B, Head Teacher.)

Very good. (Francis Cobbinah, Anyinabrim Catholic Basic, Assistant, Head Teacher).

They are very good and educative. (Isaac Zikpi, Andoe D/A Basic B Head Teacher).

The books are attractive and very easy to read. (John B Tawiah, Assin Nkran-Ngresi D/A, Head Teacher).

They are very interesting-educative, informative, entertaining and thought-provoking books. (Joseph Ato Yankson,Assin Domeabra D/A Basic, Head Teacher)

Are there suggestions/recommendations you would want to make?

I suggest the reading project extend to cover more schools for many children to benefit. (Stephen Tetteh, Librarian, Asamankese D/A).

We want more books. (Francis Amoah, Assin Manso D/A Basic B, Head teacher.)

and African storybooks. (John B Tawiah, Assin Nkran-Ngresi D/A, Head teacher).

ACKNOWLEDGEMENTS

We are grateful to Yamada for their support in helping to build the capacity of teachers and improve educational standards of children in the Assin South community in Ghana. The children who will enroll in these schools in future will profit from the new books and the new knowledge the teachers have acquired.

We wish to acknowledge the Deputy Minister for Education and Member of Parliament for the Assin South District for his support of the programme.  We also acknowledge the immense support from the Central Regional Director and District Director of the Ghana Education Service.  Without their support the programme would not have been as successful.

| BUDGET ITEMS | IBBY GHANA (US $) | IBBY YAMADA Funds (US $) | Budget GhC | Expenditure GhC | Expenditure US$ |
| --- | --- | --- | --- | --- | --- |
| Personnel Costs |  |  |  |  |  |
| - Honoraria for Coordinators | 2,880.00 |  | 16,185.60 | 16,185.60 | 2,880.00 |
| - Honoraria for Workshop Facilitators |  | 1,500.00 | 8,430.00 | 8,430.00 | 1,500.00 |
| - Travel costs for Facilitators and Coordinators |  | 1,100.00 | 6,182.00 | 6,966.00 | 1,239.50 |
| - Transport Allowance for Participants |  | 680.00 | 3,821.60 | 4,000.00 | 711.74 |
| - Meal Costs for Workshop |  | 1,200.00 | 6,744.00 | 7158.50 | 1,273.75 |
| - Accommodation for Co-ordinators and Facilitators |  | 1,050.00 | 5,901.00 | 1,200.00 | 213.52 |
| - Accommodation for 6-Member Monitoring and Evaluation Team | 1,050.00 |  | 5,901.00 | 700.00 | 124.56 |
| - Transportation for 6-Member Monitoring and Evaluation Team | 1,100.00 |  | 6,182.00 | 6,100.00 | 1,085.41 |
| - Meals for 6-Member Monitoring and Evaluation Team | 360.00 |  | 2,023.2 | 3,152.00 | 560.85 |
| - Honoraria for 6-Member Monitoring and Evaluation Team | 2,160.00 |  | 12,139.20 | 12,139.20 | 2,160.00 |

| BUDGET ITEMS | IBBY GHANA (US $) | IBBY YAMADA Funds (US $) | Budget GhC | Expenditure GhC | Expenditure US$ |
| --- | --- | --- | --- | --- | --- |
| Material Costs |  |  |  |  |  |
| General Expenses: |  |  |  |  |  |
| - Hiring of venue |  | 400.00 | 2,248.00 | 400.00 | 71.17 |
| - Communication |  | 100.00 | 562.00 | 560.00 | 99.64 |
| - Transportation of Books and workshop materials |  | 200.00 | 1,124.00 | 2,850.00 | 507.12 |
| - Promotion and Advertising |  | 650.00 | 3,653.00 | 3,322.00 | 591.10 |
| Other Material Costs |  |  |  |  |  |
| - Office Supplies |  | 600.00 | 3,372.00 | 3,047.00 | 542.17 |
| - Books to be donated | 8,000.00 |  | 44,960.00 | 44,960.00 | 8,000.00 |
| Total US$ | 15,550.00 | 7,480.00 |  |  |  |
| Total Ghc | 87,391.00 | 42,037.60 |  |  |  |
| Sub-Total | US$23,030.00 | Gh129,428.60 | 129,428.60 |  |  |
| Total Expended |  |  |  | 121,170.30 | 21,560.54 |
| Balance Leftover |  |  |  | 8,258.30 | 1,469.44 |